DIN PERSONLIGE HELSESJEF

Oslo Concierge GP

Full Business Plan & Implementation Roadmap

AI-Powered Personalised Private Medical Practice for Oslo Executives

Version 3S  |  March 2026  |  CONFIDENTIAL

# 1. Executive Summary

Din Personlige Helsesjef — 'Your Personal Health Chief' — is Norway's first AI-native concierge GP practice, designed to serve Oslo's executive market with proactive, personalised, data-driven healthcare that the Norwegian public system is structurally incapable of providing.

The practice operates on a monthly membership model with three tiers (NOK 2,500 / 5,000 / 10,000 per month), targeting a panel of 50–100 members. At full capacity, the practice generates NOK 3–6 million in annual recurring revenue at net margins of 70–80% — comparable to the best consulting or legal practices in Oslo.

The core innovation is not the service concept itself — concierge medicine is a proven global model — but the AI infrastructure layer that makes it operationally viable for a single physician. Built on locally-hosted, GDPR-compliant AI (OpenClaw on Mac Mini M4), it automates the cognitive overhead that typically requires an entire support team: between-visit monitoring, pre-consultation briefings, lab result interpretation, protocol management, and proactive member outreach. The physician focuses on the high-value clinical relationship. The AI handles everything else.

This is not a technology startup. It is a medical practice — one powered by the most sophisticated personal AI infrastructure in Norway today.

## Key Metrics at Full Operation

| Metric | Value |
| --- | --- |
| Annual Recurring Revenue | NOK 6,000,000 |
| Estimated Net Margin | 70–80% |
| Panel Size | 50–100 members (vs. 1,100+ for a standard fastlege) |
| Time Commitment | 3–4 clinical days/week |
| Break-even | ~15 members (NOK 900,000–1,125,000/year) |
| Launch Timeline | First paying members within 60–90 days |

# 2. The Market Opportunity

## 2.1  A Structural Failure at the Top End

The Norwegian fastlege system was designed for coverage, not for quality at the executive level. The average fastlege manages 1,100+ patients, delivers 10-minute consultations, has no infrastructure for between-visit contact, and operates almost entirely reactively — treating illness when it arrives rather than preventing or optimising health.

Oslo's executive class experiences this as a jarring contrast to every other premium service in their life. These are people who apply data-driven thinking to every corner of their professional existence. They have personal trainers with biometric programmes, financial advisors who know their complete picture, lawyers on retainer, executive coaches. Their health — often their most valuable asset — gets a 10-minute appointment every few years.

The problem is not access to emergency care. It is the complete absence of a long-term, proactive, personalised health relationship. That product does not exist in Norway. This practice creates it.

## 2.2  Target Market

The ideal member is 38–58, earning NOK 2M+ household income, already investing in premium wellness, and frustrated by the public system's inability to know them as an individual:

Partners and senior associates at Oslo law, finance, and consulting firms

C-suite and senior executives at Equinor, DNB, Statkraft, Kongsberg, Aker, and comparable companies

Senior management at PE/VC funds and Oslo-based family offices

Successful founders and tech entrepreneurs

High-income expats in senior Oslo roles

Professionals already spending on Oura rings, nutritionists, and personal trainers

## 2.3  Market Size

Oslo has ~700,000 inhabitants. An estimated 15,000–25,000 fit the executive profile. Reaching 100 members is less than 0.7% penetration — achievable through personal network outreach alone in Year 1.

## 2.4  Global Validation & International Analogues

Concierge medicine is proven and fast-growing globally — USD 20.5B in 2025, projected USD 44.3B by 2034. What is new — and absent in Norway — is the combination of concierge medicine with locally-hosted AI infrastructure.

| Practice | Location | Pricing | Model | Key Insight |
| --- | --- | --- | --- | --- |
| MDVIP | USA | USD 1,800–3,000/yr | Network of 1,100+ GPs, ~600 patients/doctor | Proven at scale — premium over public care |
| Parsley Health | USA/UK | USD 150–250/mo | Functional medicine + health coaching | Closest analogue — data-driven, preventive |
| One Medical | USA | USD 199/yr + insurance | App-based, now Amazon-owned | Tech integration at volume; validates market |
| Lanserhof | Germany/Austria/UK | EUR 500–1,500/day | Longevity resort, executive clientele | Validates executive appetite for premium health |
| PrivateDoc / Concierge GP | UK (London) | GBP 3,000–12,000/yr | Boutique solo GP practices | Closest structural analogue to Oslo model |
| Coa / Nemo Health | Scandinavia | NOK 600–1,500/mo | Digital primary care, limited relationship | Proves Norwegian willingness to pay |
| Aleris / Volvat | Norway | NOK 2,000–5,000/consult | Private specialist care, no retainer | Current ceiling — no ongoing relationship product |

Key insight: The most successful international concierge practices compete on depth of relationship, not price. In London and New York, practices charging USD/GBP 5,000–10,000+/year have multi-year waiting lists. Oslo has comparable purchasing power and zero competition in this segment.

# 3. The Service Model

## 3.1  Membership Tiers

| Feature | Klienten — NOK 2,500/mo | Partneren — NOK 5,000/mo | Partneren Pro — NOK 10,000/mo |
| --- | --- | --- | --- |
| Annual health assessment | 2 hours | 2 hours + advanced labs | 3 hours + full longevity panel |
| Follow-up consultations | Quarterly (4/year) | Every 2 months (6/year) | Monthly (12/year) |
| Messaging access | WhatsApp, same-day reply | WhatsApp + direct mobile | Unlimited calls + messages |
| Appointment guarantee | Same week | Same day (urgent) | Same day always |
| Lab panel | Standard annual | Advanced metabolic + cardiovascular | Full longevity panel incl. ApoB, GlycanAge |
| Wearable integration | Optional | Included (Oura/Garmin/Apple) | Included + monthly analysis |
| AI health brief | Quarterly summary | Monthly personalised report | Monthly + annual roadmap |
| Supplement protocol | On request | Included, reviewed 2x/year | Full protocol, quarterly review |
| Home/office visit | Not included | 1 per year | Unlimited |
| Travel medicine | Standard advice | Included | Full remote support abroad |
| Annual prepay discount | 10% | 10% | 10% |
| Max panel members | 40 | 40 | 20 |

## 3.2  The Core Differentiator

The differentiator is not speed of access — private Oslo clinics already offer that. The differentiator is continuity and depth. Every member has a living health dossier accumulating data across years. Every consultation builds on the last. The AI infrastructure means the physician arrives at every appointment already knowing what changed, what trends need attention, and what questions matter.

Members do not feel like patients. They feel like they have a personal health director.

## 3.3  The Annual Health Roadmap

Every Tier 2 and Tier 3 member receives a 90-minute Annual Health Roadmap Review at their membership anniversary — reviewing progress, updating risk stratification, and setting measurable objectives for the coming year. This ritual creates a powerful retention anchor. International data from comparable practices shows 40% lower churn rates among members completing annual roadmap reviews.

# 4. AI & Technology Architecture

## 4.1  The Infrastructure Advantage

The entire technology stack runs locally on Mac Mini M4 hardware. No patient data ever leaves the physician's premises — a GDPR compliance requirement and a premium marketing differentiator.

| Component | Specification |
| --- | --- |
| Hardware | Mac Mini M4 (current) → Mac Studio M5 Max 128GB (Year 2–3) |
| Orchestration | OpenClaw — local AI agent framework |
| LLM Models | Qwen 3.5 35B (local) for analysis; Claude Sonnet API for drafting (non-PII only) |
| Knowledge Base | Per-member RAG folders, markdown-structured, updated after every interaction |
| Secure Access | Cloudflare Tunnel — encrypted remote access |
| Communication | Signal/WhatsApp — end-to-end encrypted member messaging |
| Lab Integration | PDF ingestion pipeline → structured JSON → member dossier |
| Wearable Pipeline | Garmin/Oura/Apple Health → weekly structured summaries |
| Billing | Stripe or Vipps recurring membership payments |

## 4.2  The Five AI Agents

| Agent | Trigger | Function |
| --- | --- | --- |
| Nightly Monitor | 02:00 daily | Reads all member dossiers, flags anomalies vs. personal baselines, generates morning briefing |
| Pre-Consultation Briefer | 60 min before appointment | Summarises changes since last consult, suggests consultation structure |
| Lab Result Processor | New PDF in lab folder | Parses results, flags out-of-range values, drafts lay-language interpretation |
| Monthly Health Brief | 1st of each month | Synthesises wearable, consult, and messaging data into personalised health brief |
| Protocol Reviewer | Quarterly | Reviews supplement/diet/exercise protocols against latest labs, flags adjustments |

# 5. Financial Projections

## 5.1  Revenue & Net Income

|  | Year 1 (ramp) | Year 2 | Year 3 | Full Capacity |
| --- | --- | --- | --- | --- |
| Members | 35–50 | 60–75 | 80–100 | 100 |
| Monthly Revenue | NOK 175–250K | NOK 350–450K | NOK 450–500K | NOK 500K |
| Annual Revenue | NOK 2.1–3.0M | NOK 4.2–5.4M | NOK 5.4–6.0M | NOK 6.0M |
| Estimated Net (70–80%) | NOK 1.5–2.4M | NOK 2.9–4.3M | NOK 3.8–4.8M | NOK 4.2–4.8M |

Figure 1 — Annual Revenue & Net Income by Year

## 5.2  Member Growth Projection

Figure 2 — Projected Member Growth with Break-Even Threshold

## 5.3  Break-Even Analysis

Figure 3 — Monthly Revenue vs. Costs (Break-Even at ~12–15 members)

Break-even point: 15–18 members generating NOK 75,000–90,000/month vs. NOK 40,000–60,000/month costs

Timeline to break-even: 60–90 days from launch given existing professional network

Payback on setup investment: Within 6–12 months at Tier 2 average pricing

## 5.4  Revenue Mix by Tier

Figure 4 — Annual Revenue by Membership Tier

## 5.5  5-Year Financial Waterfall

Figure 5 — 5-Year Cumulative Net Income Waterfall (setup costs deducted)

## 5.6  Cost Structure

| Cost Item | Monthly | Annual |
| --- | --- | --- |
| Clinic room rental (Oslo centre) | NOK 10,000–20,000 | NOK 120,000–240,000 |
| Lab costs | NOK 5,000–15,000 | NOK 60,000–180,000 |
| OpenClaw / AI infrastructure | NOK 1,000–2,000 | NOK 12,000–24,000 |
| EPJ system (EG Pasientsky) | NOK 600–800 | NOK 7,200–9,600 |
| NPE contribution | — | NOK 1,000–2,500 |
| Professional liability insurance | — | NOK 20,000–40,000 |
| Accountant / legal | — | NOK 30,000–60,000 |
| Marketing and content | — | NOK 20,000–40,000 |
| Total (at full operation) | NOK 40,000–80,000 | NOK 480,000–720,000 |

## 5.7  Tax Structure

Register as AS (Aksjeselskap). Corporate tax rate 22%. Optimal structure: salary of NOK 700,000–900,000 with retained earnings compounding in the company. Dividends extracted at 37.84% effective rate. A skilled skatteadvokat can optimise this structure to be worth NOK 200,000–500,000/year in after-tax income.

# 6. Marketing & Customer Acquisition

## 6.1  Core Positioning

"Din personlige helsesjef — legen som faktisk kjenner deg."

This is not a healthcare pitch. It is a relationship pitch. Oslo's most successful people are missing one thing their peers in London and New York increasingly have: a doctor who actually knows them. The physician who remembers their labs from three years ago, who messages when sleep data looks concerning, who treats health as an ongoing project — not a series of 10-minute appointments.

## 6.2  Acquisition Channels

| Channel | Timeline | Target | ROI |
| --- | --- | --- | --- |
| Personal network outreach | Month 1–3 | 10–15 founding members | Highest — zero cost |
| Executive Health Audit (NOK 15,000) | Month 3+ | Corporate entry, ~40% convert to membership | High — self-funding |
| Corporate executive benefits | Month 3–6 | 5–10 Oslo companies | High — scales revenue |
| Thought leadership (Finansavisen/DN) | Ongoing | Inbound leads | High — brand-building |
| Referral programme (1 free month) | Month 4+ | Member-driven acquisition | Highest — trust transfer |
| Premium partnerships (gym, physio, coaching) | Month 6+ | Warm wellness audiences | Medium |

## 6.3  The Corporate Benefits Channel

The corporate pitch is straightforward: executive health membership as a benefit costs NOK 30,000–120,000 per executive annually — trivial against the cost of an executive vacancy (typically 1–2× annual salary). A single agreement covering five executives generates NOK 150,000–600,000 in recurring annual revenue.

Secure 2-year exclusivity agreements with one premium private clinic and one premium gym (e.g. SATS Elite). This prevents direct replication and creates a defensible referral network.

# 7. Implementation Roadmap

| Phase | Timeline | Objectives | Key Milestones |
| --- | --- | --- | --- |
| Foundation | Weeks 1–4 | Legal, systems, clinical infrastructure | AS registered, EPJ live, lab partnerships, OpenClaw configured |
| Founder Launch | Weeks 5–12 | Soft-launch to personal network | 10–15 founding members, all tiers tested, first dossiers built |
| Growth | Months 4–12 | Full-rate acquisition, corporate outreach | 40–50 members, first corporate agreement, content published |
| Scale | Year 2 | Expand capacity, add clinical support | 75–100 members, nurse practitioner/PA hired |
| Optimise | Year 3+ | Full concierge operation | 80–100 members, optional second physician or expansion |

## 7.1  90-Day Launch Checklist

Week 1: Review fastlegeavtale for competing activity clauses; consult Legeforeningen legal support if needed

Week 1: Register AS via Altinn; notify municipality of private practice; notify employer per contract

Week 1–2: Engage lawyer — membership agreement, privacy notice, consent forms

Week 1–2: Apply for ansvarsforsikring (professional liability insurance)

Week 2: Identify and secure consultation room (shared privatklinikk space to start)

Week 2–4: Set up OpenClaw on Mac Mini M4 with member dossier structure and all 5 AI agents

Week 2–4: Establish lab partnership accounts (Unilabs and/or Fürst)

Week 2–4: Register with NPE before first patient; configure EPJ, intake form, scheduling, billing

Week 4–6: Draft member handbook, supplement protocol templates, SOAP consultation templates

Week 6–8: Write personal outreach to 30–50 professional network contacts

Week 8–10: Host 2–3 informal conversations; offer founding member pricing (NOK 1,500–2,500/mo)

Week 10–12: Onboard first 5–10 members; run first agent briefing cycle

Day 90 Target: 15+ members, NOK 75,000+/month recurring revenue

# 8. Risk Management & Competitive Moat

## 8.1  Key Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Physician illness/unavailability | Low | High | 1–2 locum GP relationships; coverage dossiers; force majeure clause |
| Fastlege agreement conflict | Medium | High | Review contract before launch; clear practice separation; legal advice |
| Competitive entry | Medium | Medium | 2-year exclusive partnerships; proprietary AI stack; data moat |
| Member churn | Medium | Medium | Annual Roadmap ritual; prepay discount; engagement scoring; pause option |
| Regulatory change | Low | Medium | Monitor helfrivat rules; annual healthcare legal review |

## 8.2  Competitive Moat

| Moat Layer | Description | Time to Replicate |
| --- | --- | --- |
| Data accumulation | Member dossiers grow richer with every interaction — irreplaceable after 2+ years | 2+ years |
| AI infrastructure | The OpenClaw agent stack requires significant technical expertise to build | 12–18 months |
| Exclusive partnerships | 2-year lock-in with clinic and gym partners blocks referral network access | 24 months |
| Personal trust | The physician-member relationship is the primary retention driver — irreplaceable | Irreplaceable |

# 9. Regulatory & Legal Framework

## 9.1  Practice Structure: Helfrivat

The practice operates as a hjelprivat praksis — fully private, no public funding, no trygderefusjon. Patients pay 100% out-of-pocket. No Helfo registration required. Full pricing freedom. No normaltariff obligations.

## 9.2  Registration Requirements

| Requirement | Details | Timeline |
| --- | --- | --- |
| Business Entity | Register AS or ENK via Altinn | Week 1 |
| Municipality Notification | Notify kommune: name, address, size, financing model | Week 1–2 |
| Employer Notification | Inform municipality of secondary commercial activity | Week 1 |
| NPE Registration | Notify Norsk pasientskadeerstatning before first patient (pasientskadeloven §8) | Before first patient |
| EPJ System | Compliant electronic patient journal per pasientjournal-forskrift §4 | Week 2–4 |
| Professional Insurance | Ansvarsforsikring | Week 1–2 |

# 10. Member Retention Strategy

Retaining a member is worth NOK 30,000–120,000 per year. The retention framework is built around four principles: demonstrate ongoing value, create commitment anchors, reduce friction to staying, and make leaving feel like a genuine loss.

| Strategy | Mechanism | Target Metric |
| --- | --- | --- |
| Annual Health Roadmap | 90-min anniversary review: progress, goals, risk update | Roadmap completion >90% |
| Quarterly 'Health Win' | One concrete data-driven improvement highlighted per quarter | Engagement score >80% |
| Engagement Scoring | Track message frequency, consult attendance, wearable sync, lab completion | Monthly churn <2% |
| Pause Option | 1–3 month pause available (max 1/year); full dossier maintained | Pause-to-resume >70% |
| Referral Incentive | One free month per successful referral staying 3+ months | Referral rate >20%/year |
| Annual Prepay Discount | 10% off for 12-month upfront commitment | Annual retention >85% |

# 11. Funding & Investment Options

Din Personlige Helsesjef is operationally lean — setup costs of NOK 150,000–300,000 and a break-even of 15–18 members mean it can be self-funded by a physician with modest personal capital. However, several Norwegian and European funding options can accelerate growth and de-risk the investment.

## 11.1  Innovation Norway (Innovasjon Norge)

Innovation Norway is the primary government instrument for supporting innovative businesses. Frame the practice as Norway's first AI-native health platform — not just a GP practice. The technology angle (locally-hosted LLM, real-time biomarker monitoring, AI agent infrastructure) is what secures funding. Innovation Norway funds technology, not services; position accordingly.

| Programme | Amount | Fit |
| --- | --- | --- |
| Startup Grant (Etablerertilskudd) | NOK 500,000–900,000 | Strong — AI-native medical practice is novel; clear market gap |
| Innovation Loan (Innovasjonslån) | NOK 500,000–50M | Moderate — de-risks AI infrastructure investment |
| IFU/OFU (Industrial R&D) | Up to 50% of R&D costs | Strong — if co-developing AI with a clinic or hospital partner |
| Market Introduction Support | NOK 100,000–500,000 | Moderate — targeting Norwegian corporate market systematically |

## 11.2  Research Council of Norway (Norges Forskningsråd)

| Programme | Amount | Fit |
| --- | --- | --- |
| BIA (User-Driven Research) | NOK 1–10M over 3 years | Strong — AI in personalised medicine is a priority area |
| HelseOmsorg21 initiatives | Variable | Moderate — frame as contribution to Norwegian health tech leadership |

## 11.3  Oslo Business Region & Local Ecosystem

| Entity | Support Type | Fit |
| --- | --- | --- |
| Oslo Business Region | Mentorship, network, introductions to investors | High — Oslo-focused; health and tech sectors prioritised |
| Oslo Cancer Cluster Innovation Park | Co-location, network, AI-in-health partners | Moderate — health sector focus |
| Gründerskolen | Training, network, alumni community | Useful for business development |

## 11.4  EU Innovation Funding

| Programme | Amount | Fit |
| --- | --- | --- |
| Horizon Europe — EIC Accelerator | Up to EUR 2.5M grant + EUR 15M equity | Strong if practice scales to a replicable platform product |
| EIC Pathfinder | Up to EUR 4M | Earlier stage; suitable for AI-in-medicine research component |
| Eurostars (bilateral R&D) | Up to EUR 2M | Viable for AI development with an international partner |
| EEA/Norway Grants — Health programme | Variable | Accessible for Norwegian SMEs; health innovation focus |

## 11.5  Private Capital

| Source | Amount | Considerations |
| --- | --- | --- |
| Angel investors / HNWIs | NOK 500K–5M | Oslo health and tech angels; personal network overlaps with member target |
| Nordic health-tech VCs | NOK 5–50M (Series A) | Requires platform narrative and scalability proof; viable by Year 2–3 |
| Strategic investors (private clinic groups) | Variable | Aleris, Capio, Volvat — potential to acquire, partner, or license the AI model |
| Family offices | NOK 1–20M | Several Oslo family offices active in health and wellness |

## 11.6  Recommended Phased Approach

| Phase | Recommended Approach | Target |
| --- | --- | --- |
| Launch (Phase 0–1) | Self-fund setup; apply to Innovation Norway Startup Grant in parallel | NOK 150K–300K personal + NOK 500K–900K grant |
| Growth (Phase 2) | Reinvest cash flow; secure IFU/BIA grant for AI development | Revenue-funded + NOK 1–3M research grant |
| Scale (Phase 3+) | Evaluate strategic partnership or angel round if platform ambition exists | NOK 2–10M if applicable |

Note: The practice does not require external funding to be viable. A profitable practice by Month 3–4 is the strongest possible negotiating position for any future funding or partnership.

# 12. Setup & Investment Summary

| Category | Item | Cost (NOK) | Notes |
| --- | --- | --- | --- |
| Legal | AS registration | 5,570 | One-time |
| Legal | Lawyer (membership agreement, privacy docs) | 15,000–25,000 | One-time |
| Legal | Accountant (setup + Year 1) | 10,000–15,000 | First year |
| Insurance | Ansvarsforsikring (professional liability) | 20,000–40,000 | Annual |
| Infrastructure | Mac Mini M4 (if not owned) | 8,000–12,000 | One-time |
| Infrastructure | Clinical equipment (ECG, BP, scale) | 15,000–30,000 | One-time |
| Infrastructure | Cloudflare Tunnel + domain | 500–1,000 | Annual |
| Clinical | EPJ system (EG Pasientsky) | 7,200–9,600 | Annual |
| Clinical | NPE registration contribution | 1,000–2,500 | Annual |
| Clinical | Lab partnership setup | 0–5,000 | Variable |
| Clinical | Intake questionnaire + scheduling tools | 0–4,200 | Annual |
| Marketing | Website (can DIY) | 0–10,000 | One-time |
| Working Capital | Clinic room deposit (3 months) | 30,000–60,000 | Refundable |
| Working Capital | Operating buffer (3 months) | 50,000–100,000 | Recommended |
|  | TOTAL ESTIMATED SETUP | ~NOK 162,000–314,000 |  |

The product does not exist in Norway.

You are not competing — you are creating a category.

The global market validates the model. Oslo's executive market is ready.
The AI infrastructure exists. The only variable is execution.

Din Personlige Helsesjef  |  Oslo Concierge GP  |  CONFIDENTIAL  |  March 2026  |  v3S

# 13. Evidence-Based Supplement Protocols

Personalised supplementation is one of the highest-value deliverables in the concierge model — and one of the most under-served by the standard fastlege system, where supplementation advice is rarely biomarker-led and almost never monitored over time.

In Din Personlige Helsesjef, every supplement recommendation is driven by three inputs: the member's lab results, their wearable data trends, and their stated health goals. Protocols are reviewed at every consultation and updated quarterly. Nothing is prescribed speculatively — every recommendation is tied to a measurable clinical trigger.

## 13.1  Foundation Protocols — Applicable to Most Members

These supplements have strong evidence bases and high prevalence of need in the Oslo executive demographic:

| Supplement | Clinical Trigger | Protocol | Evidence |
| --- | --- | --- | --- |
| Vitamin D3 + K2 (MK-7) | 25-OH-D3 <75 nmol/L — extremely common in Oslo latitude | 2,000–5,000 IU D3 + 100–200 mcg K2 daily | Strong — deficiency widespread; supplementation effective and safe |
| Magnesium glycinate | RBC Mg <0.85, poor sleep, muscle cramps, stress indicators in wearable | 300–400 mg elemental Mg, evening | Strong for sleep; moderate for stress, BP, and insulin sensitivity |
| Omega-3 (EPA/DHA) | Omega-3 index <8%, elevated TG, cardiovascular risk score | 2–4 g EPA+DHA daily (high-quality fish oil) | Strong — cardiovascular, anti-inflammatory, cognitive |
| Creatine monohydrate | Cognitive performance goals, strength training, age >45 | 3–5 g daily, any time | Strong — cognitive performance, muscle health, longevity signal |
| B12 (methylcobalamin) | B12 <300 pmol/L, vegan diet, age >60, metformin use | 1,000 mcg sublingual; IM injection if severe | Strong for deficiency states |
| Zinc bisglycinate | Serum Zn <11 µmol/L, frequent illness, low testosterone pattern | 15–25 mg elemental Zn with food | Moderate — immune support, testosterone cofactor |
| Collagen peptides + Vit C | Joint symptoms, skin goals, connective tissue concerns | 10–15 g hydrolysed collagen + 50 mg vitamin C, AM | Moderate — growing evidence base |

## 13.2  Condition-Specific Protocols

| Condition / Goal | Supplement Stack | Protocol | Monitor |
| --- | --- | --- | --- |
| Elevated hsCRP / inflammation | Curcumin + piperine, high-dose Omega-3 | 500 mg curcumin 2x/day + 5 mg piperine; increase Omega-3 to 4g | Recheck hsCRP at 12 weeks |
| Sleep dysfunction | Magnesium glycinate, low-dose melatonin, ashwagandha KSM-66 | Mg 400 mg + 0.5–1 mg melatonin 30 min pre-sleep + ashwagandha 600 mg PM | HRV trend, sleep stage data via wearable |
| Subclinical low testosterone | Zinc, D3, ashwagandha, DHEA (if DHEA-S low) | Zinc 25 mg + D3 4,000 IU + ashwagandha 600 mg daily | Recheck T + SHBG at 3 months; consider TRT referral if inadequate |
| Cognitive performance / executive stress | Lion's Mane, Rhodiola rosea, L-theanine + caffeine stack | Lion's Mane 500–1,000 mg AM; Rhodiola 200 mg AM; L-theanine 200 mg with coffee | Subjective cognitive scores, wearable HRV |
| Insulin resistance / elevated HOMA-IR | Berberine, chromium, Omega-3 | Berberine 500 mg 2–3x/day with meals | Recheck fasting insulin + HbA1c at 8 weeks |
| Cardiovascular risk (elevated ApoB/Lp(a)) | High-dose niacin (if tolerated), Omega-3, plant sterols | Titrate niacin to 1–2 g/day; Omega-3 4g; psyllium husk 5–10g | Specialist referral likely required for Lp(a) |
| Iron deficiency (non-anaemic) | Ferrous bisglycinate + vitamin C | 25–50 mg elemental iron every other day + 100 mg Vit C | Recheck ferritin at 8 weeks |
| Longevity / anti-ageing | NMN or NR (NAD+ precursor), resveratrol, spermidine | NMN 500–1,000 mg AM; resveratrol 500 mg with fat | GlycanAge, HRV trends, body composition |

## 13.3  Prescribable Therapeutics (Physician-Only)

As a licensed physician, Ragnhild can prescribe therapeutics that go beyond the over-the-counter supplement range. These offer significant clinical value and represent a meaningful differentiator over non-physician wellness providers:

| Therapeutic | Indication | Mechanism | Regulatory Status |
| --- | --- | --- | --- |
| Low-dose naltrexone (LDN) | Autoimmune conditions, chronic inflammation, ME/CFS, mood disorders | Modulates endorphin system; anti-inflammatory at low doses (1.5–4.5 mg) | Prescription; off-label use — well-evidenced |
| Metformin (longevity protocol) | Insulin resistance, longevity optimisation, metabolic risk | AMPK activation, mTOR inhibition — significant longevity data emerging | Prescription; off-label for longevity |
| Testosterone replacement (TRT) | Confirmed low testosterone with symptoms | Hormone replacement; gel, injection, or cream | Prescription; refer to endocrinologist or manage in-practice |
| Thyroid optimisation (T3/T4) | Subclinical hypothyroidism, poor response to T4 alone | Direct hormone replacement | Prescription; collaborative with endocrinology |
| DHEA | Low DHEA-S confirmed on labs, adrenal insufficiency pattern | Adrenal hormone precursor | Prescription in Norway; lab-guided |
| Peptide therapies (emerging) | BPC-157 (tissue repair), Semax (cognitive), TB-500 (recovery) | Regenerative signalling molecules | Regulatory status evolving in Norway — legal review required before prescribing |

## 13.4  Supplement Revenue Model

Supplement protocols offer an optional revenue stream beyond the membership fee. Options include:

Pharmaceutical-grade supplement dispensing (white-label or partner brand) — NOK 500–3,000/month per member

Personalised supplement subscription (quarterly protocol + fulfilment) — NOK 1,500–4,000/quarter

Referral partnership with premium supplement suppliers (e.g. Thorne, Pure Encapsulations) — commission model

Annual protocol review as a standalone service — NOK 3,000–5,000 (non-members)

Note: In Norway, supplement sales by physicians are permissible but require care to avoid conflicts of interest. The safest model is to recommend specific products without financial involvement, or to operate through a clearly disclosed partnership arrangement.

# 14. Premium Optional Services — The Wellness Menu

Inspired by the Ways2Well model — a leading US concierge wellness practice offering functional medicine, IV therapy, peptides, hormone optimisation, and aesthetics — the following optional services extend Din Personlige Helsesjef beyond primary care into a comprehensive longevity and performance offering.

These services are add-ons, not membership inclusions. They are offered to members who want to go deeper, generate additional revenue per member, and significantly differentiate the practice from any competitor. As a licensed physician, Ragnhild can offer services that nurses and wellness practitioners legally cannot.

## 14.1  Wellness IV Therapy

IV therapy delivers vitamins, minerals, amino acids, and hydration directly into the bloodstream — bypassing gut absorption for immediate systemic availability. In the Oslo executive market, IV therapy is gaining traction as a performance and recovery tool. It is currently available at a handful of private clinics in Oslo at NOK 1,500–4,500 per session.

| Drip Protocol | Key Ingredients | Indication | Session Price (NOK) |
| --- | --- | --- | --- |
| Executive Performance Drip | High-dose Vit C, B-complex, Magnesium, Zinc, L-Carnitine, Glutathione | Energy, cognitive performance, stress recovery | 2,500–3,500 |
| Immunity Shield | Vit C 10g+, Zinc, Selenium, B12, Glutathione | Immune boost, pre/post travel, infection recovery | 2,000–3,000 |
| NAD+ Infusion | Nicotinamide adenine dinucleotide 250–500 mg | Cellular energy, longevity, cognitive clarity, post-illness recovery | 4,000–6,000 |
| Hydration + Recovery | Saline, Electrolytes, B-complex, Magnesium | Jet lag, post-exercise, hangover, dehydration | 1,500–2,500 |
| Longevity & Anti-Ageing | NAD+, Glutathione, Vit C, Alpha-lipoic acid, Selenium | Oxidative stress reduction, cellular repair, energy | 5,000–7,500 |
| Myers Cocktail (Classic) | Magnesium, Calcium, B-vitamins, Vit C | General wellness, fatigue, fibromyalgia, migraines | 2,000–3,000 |
| Glutathione Push | Reduced glutathione 1,200–2,400 mg IV push | Detoxification, skin brightening, antioxidant replenishment | 1,500–2,500 |
| Custom Protocol | Biomarker-led formulation | Fully personalised based on member labs | 3,000–8,000 |

Revenue potential: At 5 sessions/week across the member base: NOK 50,000–150,000/month additional revenue

Equipment required: IV stands, infusion pumps, pharmaceutical-grade supplements (Braun or Fresenius Kabi), refrigerated storage

Regulatory note: IV therapy in Norway requires physician oversight. As the prescribing physician, Ragnhild can administer or delegate to a trained nurse under medical supervision.

## 14.2  Medical Aesthetics

Medical aesthetics is a rapidly growing premium category in Oslo. Performed by a physician with a clinical framing — not a beauty salon — it commands both premium pricing and strong repeat business. The key differentiator is integrating aesthetics with health: Botox to treat migraines as well as lines; filler with collagen biomarker monitoring; skin treatments guided by inflammatory markers.

| Service | Description | Indication | Price Range (NOK) |
| --- | --- | --- | --- |
| Botox / Botulinum Toxin | Wrinkle relaxation: forehead, crow's feet, glabella, lip flip | Aesthetic — also therapeutic for migraines, hyperhidrosis, bruxism | 3,000–8,000/session |
| Dermal Fillers (HA) | Lip volume, nasolabial folds, cheek augmentation, under-eye hollow | Volume restoration, facial contouring | 4,000–12,000/area |
| Profhilo / Skin Boosters | Injectable hyaluronic acid skin remodelling — not filler | Skin laxity, hydration, texture improvement — popular 40–60 demographic | 5,000–8,000/treatment |
| Microneedling with PRP | Controlled skin injury + platelet-rich plasma from member's own blood | Skin rejuvenation, scarring, collagen stimulation | 4,000–7,000/session |
| Chemical Peels | Medical-grade peels (TCA, glycolic, Jessner's) | Pigmentation, texture, acne scarring | 2,500–5,000/session |
| Mesotherapy | Micro-injections of vitamins, amino acids, hyaluronic acid into skin | Hair loss (scalp), skin rejuvenation, localised fat reduction | 3,000–5,000/session |
| Medical-Grade Skincare Protocol | Prescription-strength retinoids, azelaic acid, topical Vit C | Anti-ageing, pigmentation, acne — physician-prescribed | 1,500–4,000/protocol |
| Hyperhidrosis Treatment | Botox to axillae, hands, or feet for excessive sweating | Therapeutic — significant quality-of-life impact | 4,000–6,000 |
| Migraine Prevention (Botox) | 31-injection protocol across head and neck every 12 weeks | Therapeutic — chronic migraine diagnosis | 6,000–9,000/cycle |

Revenue potential: A member booking 4 aesthetic appointments/year generates NOK 12,000–30,000 in additional revenue

Training required: Botox and filler courses for physicians — widely available; 1–3 day certification. Norwegian Dermatological Society and private course providers.

Regulatory note: In Norway, Botox and filler injections are restricted to licensed healthcare personnel (doctors, dentists, nurses under medical supervision) following the 2021 regulatory tightening. Physician administration is the gold standard.

## 14.3  Hormone Optimisation Programme

Hormone imbalances are among the most commonly missed contributors to executive underperformance — fatigue, weight gain, cognitive fog, mood dysregulation, sleep dysfunction. The Ways2Well model places hormone optimisation at the centre of its offering, with significant member uptake and high retention.

| Programme | Target | Approach | Price (NOK) |
| --- | --- | --- | --- |
| Male Hormone Optimisation | Testosterone, SHBG, LH, FSH, free T, DHEA-S, cortisol | Full panel → lifestyle + supplement → TRT if indicated. Quarterly monitoring. | 15,000–25,000/year (incl. labs) |
| Female Hormone Balance | Oestradiol, progesterone, testosterone, DHEA-S, cortisol, thyroid full panel | Perimenopause/menopause management; HRT where appropriate; adrenal support | 15,000–25,000/year (incl. labs) |
| Thyroid Optimisation | TSH, free T3, free T4, reverse T3, antibodies | Beyond TSH-only approach; T3/T4 combination therapy if symptomatic | 8,000–15,000/year (incl. labs) |
| Adrenal & Cortisol Programme | 4-point salivary cortisol, DHEA, morning cortisol, ACTH | Burnout pattern identification; adaptogen + lifestyle protocol | 6,000–12,000/year |
| Metabolic Health Programme | Fasting insulin, HOMA-IR, HbA1c, ApoB, Lp(a), CGM trial | Insulin resistance reversal; CGM-guided dietary changes; berberine/metformin if indicated | 10,000–18,000/year (incl. CGM) |

## 14.4  Longevity & Performance Optimisation

Inspired by the global longevity medicine movement (Peter Attia, Andrew Huberman, David Sinclair) and concierge practices like Ways2Well and Parsley Health, the longevity offering positions the practice at the cutting edge of what evidence-based medicine can offer executives who want to perform at their peak for decades.

| Service | Description | Price (NOK) |
| --- | --- | --- |
| VO2max Testing & Training Protocol | CPET or field test estimation; personalised Zone 2 and interval protocol | 5,000–8,000 (assessment + 3-month protocol) |
| Body Composition Deep Dive | DEXA scan referral + InBody + visceral fat tracking over time | 3,000–5,000 (annual programme) |
| Continuous Glucose Monitor (CGM) Trial | 14–28 day CGM with AI-guided dietary feedback and pattern analysis | 4,000–6,000 (device + interpretation) |
| Comprehensive Longevity Panel | ApoB, Lp(a), homocysteine, GlycanAge, omega-3 index, advanced thyroid, hormones, cancer screening | 8,000–15,000 (labs + full interpretation) |
| Sleep Optimisation Programme | Oura data analysis + lab review (cortisol, magnesium, melatonin) + protocol | 5,000–8,000 |
| Cognitive Performance Programme | Baseline cognitive testing + lab review + supplement/lifestyle protocol | 6,000–10,000 |
| NAD+ Optimisation Programme | Baseline NAD+ precursor protocol + quarterly IV NAD+ infusions | 20,000–30,000/year (supplements + 4 IV sessions) |
| Annual Longevity Report | Comprehensive 12-month health review; AI-synthesised trends; 5-year health roadmap | 8,000–12,000 |

## 14.5  Pricing Strategy for Premium Services

Premium services should be priced to reflect their clinical value, physician expertise, and the exclusivity of the setting — not to compete with beauty clinics or walk-in IV bars. The physician credential commands a premium.

| Pricing Principle | Application |
| --- | --- |
| Anchor high, offer packages | Present individual session prices first; offer 3-session or annual packages at 10–15% discount |
| Member pricing vs. non-member | Members receive 15–20% discount on all premium services vs. walk-in rate — reinforces membership value |
| Bundle with membership tier upgrade | Partneren Pro members receive 1 IV session/quarter included — drives tier upgrades |
| Corporate wellness packages | Negotiate annual agreements with Oslo companies — IV sessions + aesthetics + longevity panels as executive wellness benefits |
| Gift certificates | Premium gift option for spouses, partners — strong demand in Oslo corporate gifting culture |

## 14.6  Additional Revenue from Premium Services

Conservative estimates for a 50-member practice with optional service uptake of 30%:

| Service Category | Sessions/Month | Avg. Price | Monthly Revenue |
| --- | --- | --- | --- |
| IV Therapy (various protocols) | 12–20 | NOK 3,000 | NOK 36,000–60,000 |
| Medical Aesthetics (Botox/filler/skin) | 8–15 | NOK 6,000 | NOK 48,000–90,000 |
| Hormone Optimisation Programmes | 5–10 new/year | NOK 20,000/year | NOK 8,000–17,000 |
| Longevity Panels & Reports | 5–8 | NOK 10,000 | NOK 50,000–80,000 |
| Supplement Protocols (dispensed) | 15–25 members | NOK 1,500/month | NOK 22,500–37,500 |
| Total Additional Revenue |  |  | NOK 164,500–284,500/month |

At full service uptake, premium services could match or exceed core membership revenue — effectively doubling the practice's revenue potential to NOK 10–12M per year.

## 14.7  Regulatory Considerations for Premium Services in Norway

| Service | Regulatory Status | Action Required |
| --- | --- | --- |
| IV Therapy | Legal — physician must prescribe and supervise | Standard pharmaceutical procurement; sterile technique training |
| Botox / Botulinum Toxin | Restricted to licensed healthcare personnel (2021 law) | Physician can administer directly — gold standard; may delegate to nurse under supervision |
| Dermal Fillers | Restricted to licensed healthcare personnel (2021 law) | Same as Botox — physician administration preferred |
| Hormone Prescribing (TRT, HRT) | Prescription required; physician authority | Standard prescribing rights; document clinical indication thoroughly |
| Peptide Therapies (BPC-157 etc.) | Regulatory status unclear in Norway — grey area | Legal review required; prescribe with caution; document clinical rationale |
| NAD+ IV Infusions | Legal as physician-administered IV | Source pharmaceutical-grade NAD+ from licensed supplier |
| Medical-grade skincare (retinoids) | Prescription strength requires physician | Standard prescribing; document clinical indication |
| CGM Prescribing | Prescription in Norway for non-diabetic use | Off-label; document clinical rationale; patient consent |

Key insight: Being a physician is the licence that makes all of this possible. The 2021 Norwegian law restricting aesthetic injectables to licensed healthcare personnel effectively eliminated non-physician aesthetic providers from the premium market. This is a competitive advantage, not a barrier.

The product does not exist in Norway.

You are not competing — you are creating a category.

The global market validates the model. Oslo's executive market is ready.
The AI infrastructure exists. The only variable is execution.

Din Personlige Helsesjef  |  Oslo Concierge GP  |  CONFIDENTIAL  |  March 2026  |  v3S