## 📊 Dashboard
STATKRAFT PROCUREMENT AI — VALUE MEASUREMENT DASHBOARD
Last Updated: 17 March 2026 ¦ All values in EUR unless stated ¦ Statkraft Procurement AI Programme
KPI SUMMARY
Initiative | Category | Status | Baseline KPI | Target KPI | Current KPI | % Achieved | Est. EUR Saved | ROI | Go-Live Date | Next Review | RAG
Spend Classification | Data Quality | 🟡 Pilot | 65% accuracy | 85% accuracy |  |  |  |  | 2026-04-01 | 2026-07-01 | 🟡
Contract NLP Scanning | Contract Mgmt | 🟡 Pilot | Manual review | 80% faster |  |  |  |  | 2026-04-15 | 2026-07-15 | 🟡
Supplier Monitoring | Risk Mgmt | 🟡 Pilot | Annual review | Continuous |  |  |  |  | 2026-05-01 | 2026-08-01 | 🟡
RFQ Drafter | Sourcing | 🔵 Planned | 8 hrs/event | 2 hrs/event |  |  |  |  | 2026-07-01 | 2026-10-01 | 🔵
Demand Forecasting MRO | MRO | 🔵 Planned | Reactive only | 6-12m forecast |  |  |  |  | 2026-07-15 | 2026-10-15 | 🔵
Negotiation Pack Builder | Sourcing | 🔵 Planned | Manual prep | AI-assisted |  |  |  |  | 2026-08-01 | 2026-11-01 | 🔵
Category Strategist | Strategy | 🔵 Planned | Weeks to draft | Days to draft |  |  |  |  | 2026-09-01 | 2026-12-01 | 🔵
CSRD Compliance Agent | Compliance | 🔵 Planned | Manual checks | Automated |  |  |  |  | 2026-10-01 | 2027-01-01 | 🔵
PROGRAMME TOTAL

## 💰 Value Calculator
PROCUREMENT AI VALUE CALCULATOR — Enter yellow cells. Green cells calculate automatically.
Input Parameter | Your Value | Unit | Source / Assumption
Total annual procurement spend (EUR) | 500000000 | EUR | Statkraft internal
Number of sourcing events per year | 250 | events/yr | Statkraft estimate
Average hours per sourcing event (RFQ to award) | 40 | hrs | Industry avg
Number of contracts in portfolio | 1200 | contracts | Statkraft estimate
Hours to manually review one contract | 4 | hrs | Industry avg (Luminance benchmark)
Number of suppliers actively monitored | 200 | suppliers | Statkraft target
Annual cost of manual supplier reviews | 150000 | EUR/yr | Statkraft estimate
Procurement headcount (FTEs) | 45 | FTEs | Statkraft internal
Average fully-loaded FTE cost (EUR/yr) | 120000 | EUR/yr | Statkraft HR data
Current spend classification accuracy | 65% | % | Current state
SECTION 2: CALCULATED VALUE (auto-calculated from inputs above)
Use Case | Metric | Current State | With AI | Annual Saving (EUR) | ROI Assumption
RFQ Generation | Hours saved per event |  |  |  | 75% time reduction (Ørsted benchmark)
Contract NLP Review | Hours per contract review |  |  |  | 80% faster (Luminance / Icertis benchmark)
Supplier Monitoring | Annual monitoring cost |  |  |  | 70% cost reduction (continuous vs annual review)
Spend Classification | Classification accuracy |  |  |  | 5% spend recovery per accuracy point gained
Demand Forecasting (MRO) | Emergency premium spend |  |  |  | 50% reduction in emergency buys (Vattenfall benchmark)
Negotiation Preparation | Sourcing events with full data pack |  |  |  | 0.2% additional savings from better-prepared negotiations
Category Strategy | Strategies completed per year |  |  |  | 0.5% strategic savings from better category coverage
CSRD Compliance | Manual compliance checks |  |  |  | 4 hrs per check vs 0.1 automated equiv.
TOTAL ESTIMATED ANNUAL VALUE
Estimated programme cost (annual, EUR) |  |  |  | 750000
NET ANNUAL VALUE
ROI (x)

## 🎯 Use Case Prioritiser
USE CASE PRIORITISATION MATRIX — Score each use case 1–5 on each dimension. Priority Score auto-calculates.
SCORING WEIGHTS (adjust to reflect Statkraft priorities — must sum to 100%)
|  | 40% | 20% | 15% | 15% | 10%
|  | Business Value (40%) | Implementation Speed (20%) | Data Availability (15%) | Risk (15%) | Strategic Fit (10%)
Use Case | Category | Business Value (1-5) | Implementation Speed (1-5) | Data Availability (1-5) | Risk Score (1-5, 5=low risk) | Strategic Fit (1-5) | PRIORITY SCORE | Rank | Recommended Track | Effort (weeks) | Est. Saving (EUR/yr) | Notes
Spend Classification | Data Quality | 5 | 4 | 4 | 5 | 4 |  |  | Track B | 4–6 |  | Foundation for all other AI use cases
Contract NLP Scanning | Contract Mgmt | 5 | 4 | 3 | 5 | 4 |  |  | Track B | 6–8 |  | Immediate portfolio value, no supplier risk
Supplier Monitoring | Risk Mgmt | 5 | 3 | 4 | 4 | 5 |  |  | Track D | 8–10 |  | Manu Forti product — continuous monitoring
RFQ Generation | Sourcing | 5 | 4 | 4 | 4 | 5 |  |  | Track D | 8–12 |  | 4–8 hrs saved per event, proven at Ørsted/BP
Demand Forecasting MRO | MRO | 4 | 3 | 3 | 4 | 4 |  |  | Track D | 12–16 |  | Vattenfall 6-12m horizon benchmark
Negotiation Pack Builder | Sourcing | 5 | 3 | 4 | 4 | 4 |  |  | Track D | 10–14 |  | Market data + BATNA + walk-away
Category Strategy Agent | Strategy | 5 | 2 | 4 | 3 | 5 |  |  | Track D | 16–20 |  | Highest value — weeks → days to draft
CSRD Compliance Agent | Compliance | 4 | 3 | 3 | 3 | 5 |  |  | Track D | 12–16 |  | Mandatory for CSRD 2026 reporting
Invoice Processing | P2P | 3 | 5 | 4 | 5 | 3 |  |  | Track B | 4–6 |  | 3-way match + anomaly detection
Market Price Intelligence | Market Intel | 4 | 5 | 5 | 5 | 3 |  |  | Track A | 2–4 |  | Daily briefings on commodity indices
Supplier Onboarding | Supplier Mgmt | 3 | 3 | 3 | 4 | 3 |  |  | Track C | 10–14 |  | Automated due diligence
Contract Drafting Assist | Contract Mgmt | 4 | 2 | 4 | 3 | 4 |  |  | Track C | 14–18 |  | 40-60% legal cycle time reduction

## 📋 Initiative Tracker
INITIATIVE TRACKER — One row per AI initiative. Update monthly.
ID | Initiative Name | Track | Owner | Phase | Start Date | Go-Live Date | 90-Day Review | Baseline KPI | Target KPI | Current KPI | EUR Saved (actual) | Status | Blockers / Notes
P-001 | Spend Classification Cleanup | B | [Procurement Lead] | Pilot | 2026-04-01 | 2026-06-01 | 2026-09-01 | 65% accuracy | 85% accuracy |  |  | 🟡 In Progress | Awaiting SAP API access
P-002 | Contract NLP Scanning | B | [Category Manager] | Planned | 2026-04-15 | 2026-06-15 | 2026-09-15 | 4 hrs/contract | 45 min/contract |  |  | 🔵 Planned | Tool selection in progress
P-003 | Supplier Monitoring Agent | D | [Risk Manager] | Planned | 2026-05-01 | 2026-07-01 | 2026-10-01 | Annual review | Continuous |  |  | 🔵 Planned | Jaggaer API mapping needed

## 🖥️ Hardware & Costs
ON-PREMISES AI HARDWARE & TOTAL COST ESTIMATOR
TIER 1: ON-PREMISES INFERENCE SERVER (CONFIDENTIAL data)
Component | Specification | Qty | Unit Cost (EUR) | Total Cost (EUR) | Annual Maintenance | Notes
GPU Server | NVIDIA DGX H100 (8×H100 80GB) or Dell PowerEdge R760xa | 1 | 150000 |  |  | Runs Llama 3.3 70B / Mistral 3 comfortably
GPU (alternative) | 2× NVIDIA A100 80GB PCIe in standard server (budget path) | 1 | 45000 |  |  | Sufficient for most procurement tasks
CPU Server (orchestration) | Dell PowerEdge R650 or HP ProLiant DL380 | 2 | 8000 |  |  | Runs OpenClaw, LangChain, vector DB
NVMe Storage | 4TB NVMe SSD array for model weights + vector DB | 2 | 3000 |  |  | Llama 3.3 70B = ~140GB; embeddings storage
Network Switch | 10GbE managed switch for VLAN isolation | 1 | 2500 |  |  | Dedicated VLAN for AI inference layer
UPS | APC Smart-UPS 3000VA | 2 | 1800 |  |  | Power protection for inference servers
Rack | 42U server rack with PDU and cable management | 1 | 1200
HARDWARE TOTAL (CAPEX)
SOFTWARE LICENCES & RUNNING COSTS (ANNUAL OPEX)
Software / Service | Description | Licence Model | Annual Cost (EUR) | Notes
Ollama / vLLM | LLM inference runtime for on-prem models | Open Source | 0 | Free — self-hosted
Llama 3.3 / Mistral | Foundation LLM models | Open Source (Meta/Mistral) | 0 | Free weights — no per-token cost
OpenClaw | Agent orchestration platform | npm install | 0 | Open source — self-hosted
ChromaDB / Qdrant | Vector database for RAG / document retrieval | Open Source | 0 | Self-hosted on CPU server
LangChain | Agent workflow and RAG framework | Open Source | 0 | Python library
ELK Stack | Elasticsearch + Logstash + Kibana for audit logs | Open Source / Cloud | 3600 | €300/month Elastic Cloud basic tier
Grafana | Real-time monitoring dashboard | Open Source | 0 | Self-hosted
Docker / Kubernetes | Container orchestration for agent sandboxing | Open Source | 0 | Rancher Desktop or K3s
Azure OpenAI (Tier 2) | Private cloud LLM for INTERNAL data (EU region) | Pay-per-token | 24000 | ~€2K/month for moderate usage
ElevenLabs | Voice AI for conversational agent interface | API subscription | 1800 | Professional plan ~€150/month
Power BI / Tableau | Dashboard and reporting for value measurement | Existing licence | 0 | Use existing Statkraft licence
Maintenance / IT FTE | 0.5 FTE internal IT support for AI infrastructure | Internal | 60000 | 0.5 × €120K fully loaded FTE
ANNUAL SOFTWARE / OPEX TOTAL
TOTAL COST OF OWNERSHIP SUMMARY
Year 1 CAPEX (hardware) |  |  |  |  | One-time hardware investment
Year 1 OPEX (software + IT) |  |  |  |  | Annual running costs
Year 1 TOTAL INVESTMENT
Year 2+ annual cost |  |  |  |  | Maintenance + OPEX only
3-Year Total Cost of Ownership
Estimated Annual Value (from Value Calculator)
3-Year Net ROI